## ProjectTeam
Name | GitHub Alias
Andi Ademi | AndiPandy
Yann Gund | gundyann
Yanick Gehri | gehry1
Luca Leuenberger | Cryler
Andy Landolt | landyandolt
Amir Khalife | Brethart94

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Admission patient | A patient who's never been at our facilities before will need to be admitted with all the required identifying personal data | high | 16 |  |  | waiting
2 | Admission case | For an already admitted patient, a corresponding case has to be opened | high | 8 |  |  | waiting
3 | Editing information Pat + Case | The registered information in our system need to be editable | medium | 8 |  |  | waiting
4 | Calendar | The patients sessions need to be represented in a calendar | high | 16 |  |  | waiting
5 | Reminder | As a user I need to be able to activate the functionality to remind the patients via a reminder method | low | 16 |  |  | waiting
6 | Warning | If a patient with a contagious disease or tendency to violence is about to enter our facilities, the system needs to be able to send a corresponding warning message to the user | low | 4 |  |  | waiting
7 | Medical history | After or during an appointment, the results need to be recorded | medium | 16 |  |  | waiting
8 | Statistics | The medical data and recordings need to be visualizable in form of statistics | low | 8 |  |  | waiting
9 | Search patient or case | The user wants to be able to find a patient or case via a search function | medium | 16 |  |  | waiting
10 | Image taking | The user wants to be able to take pictures of the patients well-being | low | 4 |  |  | waiting
11 | Image comparison | The user wants to compare before and after pictures to make conclusions regarding the progress | low | 4 |  |  | waiting
12 | Archiving | Data, which will (most likely) no longer be used, needs to be able to be archived in order to avoid a cluttering of the main interface | low | 16 |  |  | waiting
13 | Log-In | An authentification method to ensure that only authorized user can access the application | low | 16 |  |  | waiting
14 | Log-Out | Authorized user need to log-out to ensure that no unauthorized user accesses the application after them | low | 4 |  |  | waiting

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
| 1 | User Obj | User model needs to be created | Database |  |  |  | 4 |  |  | waiting
| 1 | User registration | User need to be able to be added to the user database | UI, Controller |  |  |  | 4 |  |  | waiting
| 1 | Authentification | Authentification of the registered user to see if user is authorized | UI, Controller |  |  |  | 8 |  |  | waiting
| 1 | Patient Obj | Patient model needs to be created | Database |  |  |  | 4 |  |  | waiting
| 1 | Case Obj | Case model needs to be created | Database |  |  |  | 4 |  |  | waiting
| 1 | Admission Pat | A new patient should be added to the Patient database | UI, Controller |  |  |  | 8 |  |  | waiting
| 1 | Admission Case | A new case should be added to the Patient database | UI, Controller |  |  |  | 8 |  |  | waiting
| 1 | Edit Pat + Case | Patient and case information need to be editable, therefore accesibale via an "Edit" button | UI, Controller |  |  |  | 8 |  |  | waiting
| 1 | Calendar Obj | Calender model needs to be created | Database | Ademi |  |  | 4 |  |  | waiting
| 1 | Input Cal | Calender needs to have an input command, which refers to the corresponding case | UI, Controller | Ademi |  |  | 4 |  |  | waiting
| 1 | Delete Cal | Calender needs to have a delete command, which deletes the corresponding case | UI, Controller | Ademi |  |  | 4 |  |  | waiting
| 1 | Edit Cal | Calendar needs to have an edit command, which edits existing cases | UI, Controller | Ademi |  |  | 4 |  |  | waiting
| 1 | GUI Part1 |  | UI, Controller | Gehri
| 1 | GUI Part2 |  | UI, Controller | Leuenberger
| 1 | Create Database |  | Database | Landolt
| 1 | GUI Calendar |  | UI, Controller | Gund
| 1 | Institution Obj | Homescreen of Application with Navigation to all Functions | UI, Controller | Gund

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2015-09-15 | 200 | 200
1 | 2015-09-16 | 190 | 180