## ProjectTeam
Name | GitHub Alias
Andi Ademi | AndiPandy
Yann Gund | gundyann
Yanick Gehri | gehry1
Luca Leuenberger | Cryler
Andy Landolt | landyandolt
Amir Khalife | Brethart94

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
| 1 | Person Model | A person model needs to be created, in order to be used for further models | Database | Gehri | Gund |  | 1 |  | 1 | done
| 2 | Patient Model | Patient model needs to be created | Database | Gehri | Gund |  | 4 | 7 | 6 | done
| 2 | Case Model | Case model needs to be created | Database | Ademi | Landolt |  | 4 |  | 2 | done
| 3 | View New Patient | GUI new patient view | UI | Gehri | Leuenberger |  | 3 |  | 5 | done
| 2 | View Patient | GUI patient view | UI | Leuenberger | Gehri |  | 1 |  | 1 | done
| 1 | View Session | GUI session view | UI | Leuenberger | Gehri |  | 2 |  | 3 | done
| 1 | View New Session | GUI new session view | UI | Leuenberger | Gehri |  | 3 |  | 5 | done
| 1 | View Diagram | GUI diagram view | UI | Leuenberger | Gehri |  | 1 |  | 1 | done
| 2 | Create Database |  | Database | Landolt |  |  | 4 |  | 4 | cancelled
| 2 | Create Database |  | Database | Gehri | Gund |  | 3 |  | 4 | done
| 1 | Institution Model | Model of the Institution | Database | Gund | Gehri |  | 2 |  | 2 | done
| 1 | Institution View | GUI Homescreen | UI | Gund | Leuenberger |  | 2 |  | 2 | done
| 1 | Institution Presenter | Presenter for the Institution | Utility | Gund | Leuenberger |  | 2 |  | 3 | done
| 1 | Medical Reports Model | Medical Reports Model needs to be created | Database | Ademi | Landolt |  |  |  | 1 | done
| 1 | Settings View | GUI Settings for Homescreen | UI | Gund | Gehri |  | 2 |  | 3 | done
| 2 | Diagram function | Extern diagram function | UI | Leuenberger |  |  | 5 |  | 2 | cancelled
| 2 | Session Model | DB connection for SessionModel Class | Database | Landolt |  |  | 2 |  | 4 | cancelled
| 2 | Session Model | Model for the Session | Utility | Leuenberger | Gund |  | 3 |  | 3 | done
| 2 | Session Entity | Entity for the Session | Utility | Leuenberger | Gund |  | 1 |  | 1 | done
| 2 | Patient Model | Model for Patient | Database | Gehri | Gund |  | 5 |  | 5 | done
| 2 | Registration View | Gui for a new registration | UI | Gund | Gehri |  | 1 |  | 1 | done
| 3 | Service Class EM | Manager for the database connection | Utility | Gund | Gehri |  | 2 |  | 3 | done
| 2 | Calendar View | GUI Calendar | UI | Gund | Leuenberger |  | 4 | 8 | 9 | done
| 2 | Calendar Model | Calender model needs to be created | Database | Gund | Gehri |  | 4 |  | 4 | done
| 2 | Address Model | An address model needs to be created, in order to be used for further models | Database | Gund | Gehri |  | 1 |  | 1 | done
| 2 | Calendar Presenter | Presenter for the Calendar | Utility | Gund | Landolt |  | 3 |  | 3 | done
| 3 | Registration Presenter | Presenter for the Registration | Utility | Gund | Gehri |  | 4 |  | 4 | done
| 3 | Login view & model | Login with logic for the application | Utility | Gund | Leuenberger |  | 4 |  | 4 | done
| 3 | Session Model | Persisting the Sessions to a Patient | Utility | Gund | Leuenberger |  | 3 |  | 2 | done
| 3 | Styling | Styling several Classes with css | Styling | Gund | Leuenberger |  | 2 |  | 2 | done
| 3 | Patient Filter | Show and filter all patient | Utility | Gehri | Leuenberger |  | 7 |  | 8 | done
| 3 | New Patient Validation | Input validation for new patient | Utility | Gehri | Leuenberger |  | 2 |  | 3 | done
| 3 | Delete Patient function | Registered patients can be deleted | Utility | Gehri | Gund |  | 3 |  | 3 | done
| 3 | View Session | Edit Session view | UI | Leuenberger | Gund |  | 4 |  | 5 | done
| 3 | Patient Entity | Create patient and person entity | Utility | Gehri | Gund |  | 2 |  | 2 | done
| 3 | View Patient | Edit Patient view | UI | Gund | Gehri |  | 4 |  | 5 | done

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Patient management |  | high | 20 | 35 | 38 | done
2 | Session management |  | high | 12 | 25 | 29 | done
4 | Calendar |  | high | 16 | 20 | 16 | done
5 | Reminder |  | low | 16 |  |  | cancelled
6 | Warning |  | low | 4 |  |  | cancelled
7 | Medical history |  | medium | 16 |  |  | cancelled
8 | Statistics |  | low | 8 |  |  | cancelled
9 | Image management |  | low | 4 |  |  | cancelled
11 | Authentification |  | low | 16 |  | 9 | done
12 | Database |  | medium | 16 | 12 | 11 | done

## BurndownChart
Sprint | Planned Effort (h) | Time of Record (h) | Remaining Effort (h) | Remaining Ressources (d) | Summary: | Sprint | Planned (h) | Time of Record (h) | Remaining Effort after sprint (h)
1 | 15 | 9 | 21 | 21 |  | 1 | 9 | 30 | 0
1 |  | 7 | 14 | 14 |  | 2 | 45 | 50 | 0
1 |  | 14 | 0 | 7 |  | 3 | 40 | 41 | 0
Effective Effort | 21
Sprint | Planned Effort (h) | Time of Record (h) | Remaining Effort (h) | Remaining Ressources (d)
2 | 45 | 0 | 45 | 21
2 |  | 15 | 30 | 18
2 |  | 15 | 17 | 10
2 |  | 17 | 3 | 2
|  | 3 | 0
Effective Effort | 50
Sprint | Planned Effort (h) | Time of Record (h) | Remaining Effort (h) | Remaining Ressources (d)
3 | 40 | 0 | 40 | 21
3 |  | 9 | 31 | 18
3 |  | 9 | 22 | 14
3 |  | 4 | 18 | 8
3 |  | 15 | 3 | 7
3 |  | 4 | 0 | 2
Effective Effort | 41